## Team
Initials | First | Last | Email | GitHub Username
JC | Julia | Cahn | jcahn@stevens.edu | jcahn123
AV | Aaron | Vo | dvo@stevens.edu | vodewey12
AS | Ashish | Singh | asingh47@stevens.edu | ashish-python
|  |  | GitHub Repository: | https://github.com/ashish-python/SSW555tmAaronAshishJulia2019Fall/

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US04 | Marriage before divorce | JC | Complete
1 | US05 | Marriage before death | JC | Complete
1 | US42 | Reject illegitimate dates | AS | Complete
1 | US38 | List upcoming birthdays | AS | Complete
1 | US22 | Unique IDs | AV | Complete
1 | US01 | Dates before current date | AV | Complete
2 | US06 | Divorce before death | JC | Complete
2 | US07 | Less then 150 years old | JC | Complete
2 | US36 | List recent deaths | AS | Complete
2 | US35 | List recent births | AS | Complete
2 | US08 | Birth before marriage of parents | AV | Complete
2 | US16 | Male last names | AV | Complete
3 | US09 | Birth before death of parents | JC | Complete
3 | US11 | No bigamy | JC | Complete
3 | US30 | List living married | AS | Complete
3 | US31 | List living single | AS | Complete
3 | US23 | Unique name and birth date | AV | Complete
3 | US24 | Unique families by spouses | AV | Complete
4 | US15 | Fewer than 15 siblings | JC | Incomplete
4 | US21 | Correct gender for role | JC | Incomplete
4 | US29 | List deceased | AS | Incomplete
4 | US34 | List large age differences | AS | Incomplete
4 | US18 | Siblings should not marry | AV | Incomplete
4 | US17 | No marriages to children | AV | Incomplete

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2019-09-15 | 24 |  | 0
Sprint 1 | 2019-09-29 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2019-10-13 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2019-10-27 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2019-11-10 | 0 | 6 | 1100 | 145 | 148.9655

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-09-15 | 24 |  | 0
2019-09-29 | 18 | 6 | 73 | 410 | 10.6829
2019-10-13 | 12 | 6 | 86 | 390 | 13.2308
2019-10-27 | 6 | 6 | 119 | 840 | 8.5
2019-11-10 | 6

## Example Sprint
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US03 | Birth before death | hm | Done | 150 | 60 | 120 | 90 | 2014-09-24 | gedcom.py | us03_birth_b4_death | 33-36 | test03.py | test_us03 | 15-23
T03.01 | Store birth date | hm
T03.02 | Store death date | hm
T03.03 | Compare birth and death dates | hm
US05 | Marriage before death | gh | Coding | 200 | 120 |  |  |  | gedcom.py | us05_marr_b4_death | 33-36 | test05.py | test_us05 | 29-34
T05.01 | Find marriage record for individual | gh(at) | Done
T05.02 | Find marriage date | gh
T05.03 | Compare marriage date to birth date | gh(hm)
Review Results
Keep doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter

## Sprint 1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US04 | Marriage before divorce | JC | Done | 8 | 60 | 9 | 60 | 2019-09-24 | Project.py | us_04 | 209-217 | TestStuite.py | test_us04 | 49-54
US05 | Marriage before death | JC | Done | 8 | 60 | 16 | 60 | 2019-09-26 | Project.py | us_05 | 220-235 | TestStuite.py | test_us05 | 58-62
US42 | Reject illegitimate dates | AS | Done | 30 | 180 | 9 | 90 | 2019-09-29 | Project.py | us_42 | 158-164 | TestStuite.py | test_us42 | 21-28
US38 | List upcoming birthdays | AS | Done | 30 | 180 | 12 | 120 | 2019-09-29 | Project.py | us_38 | 167-178 | TestStuite.py | test_us38 | 11-17
US22 | Unique IDs | AV | Done | 8 | 60 | 1 | 20 | 2019-09-27 | Project.py | us_22 | 59 | TestStuite.py | test_us22 | 42-45
US01 | Dates before current date | AV | Done | 20 | 60 | 26 | 60 | 2019-09-27 | Project.py | us_01 | 181-206 | TestStuite.py | test_us01 | 32-38
Keep doing:
Pair programming
Weekly meet up
Messaging when github is updated
Avoid:
Last minute meetings
Complete user stories near the end of the sprint so there's little time to review and test

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US06 | Divorce before death | JC | Complete | 20 | 45 | 16 | 60 | 2019-10-07 | Project.py | us_06 | 313-328 | TestStuite.py | test_us06 | 103-107
US07 | Less then 150 years old | JC | Complete | 20 | 60 | 14 | 60 | 2019-10-07 | Project.py | us_07 | 331-345 | TestStuite.py | test_us07 | 111-117
US36 | List recent deaths | AS | Complete | 30 | 120 | 11 | 60 | 2019-10-02 | Project.py | us_36 | 243-253 | TestStuite.py | test_us36 | 66-72
US35 | List recent births | AS | Complete | 30 | 120 | 11 | 60 | 2019-10-02 | Project.py | us_35 | 256-266 | TestStuite.py | test_us35 | 77-83
US08 | Birth before marriage of parents | AV | Complete | 20 | 30 | 17 | 120 | 2019-10-06 | Project.py | us_08 | 275-291 | TestStuite.py | test_us08 | 87-91
US16 | Male last names | AV | Complete | 20 | 30 | 17 | 30 | 2019-10-06 | Project.py | us_16 | 294-310 | TestStuite.py | test_us16 | 95-99
Keep doing:
Complete user stories early so there's time to discuss any issues, time to review and merge with the master branch
Weekly meet up
Messaging when github is updated
Avoid:
Last minute meetings

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US09 | Birth before death of parents | JC | Complete | 15 | 120 | 29 | 120 | 2019-10-25 | Project.py | us_09 | 390-419 | TestStuite.py | test_us09 | 159-165
US11 | No bigamy | JC | Complete | 15 | 120 | 32 | 180 | 2019-10-25 | Project.py | us_11 | 423-455 | TestStuite.py | test_us11 | 169-173
US30 | List living married | AS | Complete | 15 | 120 | 10 | 120 | 2019-10-14 | Project.py | us_30 | 361-371 | TestStuite.py | test_us30 | 121-125
US31 | List living single | AS | Complete | 15 | 120 | 9 | 120 | 2019-10-14 | Project.py | us_31 | 374-383 | TestStuite.py | test_us31 | 130-136
US23 | Unique name and birth date | AV | Complete | 8 | 30 | 10 | 120 | 2019-10-27 | Project.py | us_23 | 458-468 | TestStuite.py | test_us23 | 140-147
US24 | Unique families by spouses | AV | Complete | 8 | 30 | 29 | 180 | 2019-10-27 | Project.py | us_24 | 471-500 | TestStuite.py | test_us24 | 151-155
Keep doing:
Pair programming
Reviewing with TA
Avoid:
Trying to fix at the last minute
Updating sheets late
Waiting till the end of Sprint to complete the stories

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US15 | Fewer than 15 siblings | JC | Incomplete | 15 | 120
US21 | Correct gender for role | JC | Incomplete | 8 | 90
US29 | List deceased | AS | Incomplete | 10 | 90
US34 | List large age differences | AS | Incomplete | 15 | 90
US18 | Siblings should not marry | AV | Incomplete | 25 | 120
US17 | No marriages to children | AV | Incomplete | 25 | 120

## Stories
Story ID | Story Name | Story Description | Owner
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | AV
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage | JC
US05 | Marriage before death | Marriage should occur before death of either spouse | JC
US06 | Divorce before death | Divorce can only occur before death of both spouses | JC
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people | JC
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce) | AV
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father | JC
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse | JC
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family | JC
US16 | Male last names | All male members of a family should have the same last name | AV
US17 | No marriages to children | Parents should not marry any of their children | AV
US18 | Siblings should not marry | Siblings should not marry one another | AV
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female | JC
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | AV
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | AV
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file | AV
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file | AS
US30 | List living married | List all living married people in a GEDCOM file | AS
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file | AS
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse | AS
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days | AS
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days | AS
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days | AS
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate) | AS